AI Website Builder — HTML/CSS Model v1.0

Complete Technical Project Document & 30-Day Development Plan

Project type: AI-powered website generation
Initial scope: Text prompt → HTML + CSS → live preview
Developer: Solo developer / beginner-to-intermediate
Initial platform: Windows PC
Primary language: Python
Base AI model: Qwen2.5-Coder-3B-Instruct
Training approach: Pretrained model first, optional LoRA fine-tuning later
Project duration: 30 days
Target result: Working MVP (Minimum Viable Product)

1. Project Overview

1.1 Project ka objective

Ek AI system develop karna hai jo natural-language prompts ko samjhe aur unki madad se complete HTML/CSS websites generate kare.

Example user prompt:

"Create a modern technology company website with a dark theme, blue gradients, responsive navbar, hero section, services cards, pricing section, and contact form."

Expected output:

- Complete index.html

- Complete style.css

- Responsive layout

- Modern visual design

- Functional navigation links

- Browser preview

- Downloadable source code

- Prompt ke through existing design ko modify karne ki facility

1.2 Initial version mein kya hoga?

Version 1.0 features:

- Prompt input interface.

- HTML/CSS code generation.

- Code editor.

- Live website preview.

- HTML aur CSS download.

- Regenerate design option.

- Follow-up prompt se website modifications.

- Basic validation aur error handling.

Initial version mein kya nahi hoga:

- React/Next.js project generation.

- Backend/database generation.

- Complete autonomous coding agent.

- Custom foundation model from scratch.

- Production-grade hosting platform.

- Multiple users ke liye billing system.

Ye features future versions mein add honge.

2. System Architecture

System ko chaar major layers mein divide kiya jayega.

Layer A — Frontend

Technologies:

- HTML

- CSS

- JavaScript

Frontend ke andar:

- Prompt input field

- Generate button

- Loading indicator

- Code editor

- Preview panel

- Download buttons

- Error display

Layer B — Backend

Technology: Python + FastAPI.

Backend responsibilities:

- User prompt receive karna.

- Prompt ko validate karna.

- AI model ko request bhejna.

- Generated code receive karna.

- HTML/CSS output extract karna.

- Basic code validation karna.

- Frontend ko result return karna.

Layer C — AI inference engine

Initial model:

Qwen/Qwen2.5-Coder-3B-Instruct

Possible local runtime: Ollama, provided ke selected model aur runtime compatible hon.

Alternative: Hugging Face Transformers.

AI inference engine prompt ko model ke input mein convert karega aur generated tokens ko HTML/CSS response mein return karega.

Layer D — Dataset and evaluation

Is layer mein:

- Prompt/code examples

- Website templates

- Training examples

- Validation examples

- Test prompts

- Quality metrics

- Error reports

store aur manage kiye jayenge.

Complete workflow

User prompt → Frontend → FastAPI backend → AI model → Generated HTML/CSS → Validation → Preview → Download.

3. Technology Stack

| Component | Recommended technology |
| --- | --- |
| Frontend | HTML, CSS, JavaScript |
| Backend | Python |
| API framework | FastAPI |
| AI model | Qwen2.5-Coder-3B-Instruct |
| Local model runtime | Ollama or Transformers |
| Code editor | Monaco Editor or CodeMirror |
| Preview | Sandboxed iframe |
| Dataset | JSONL |
| Model adaptation | Hugging Face Transformers + PEFT |
| Version control | Git + GitHub |
| Testing | Pytest + browser automation |
| Deployment later | Docker + cloud hosting |

Suggested project directory

ai-website-builder/

│

├── frontend/

│   ├── index.html

│   ├── style.css

│   └── app.js

│

├── backend/

│   ├── main.py

│   ├── model_service.py

│   ├── prompt_builder.py

│   ├── code_validator.py

│   └── schemas.py

│

├── data/

│   ├── raw/

│   ├── processed/

│   ├── train.jsonl

│   ├── validation.jsonl

│   └── test.jsonl

│

├── training/

│   ├── prepare_dataset.py

│   ├── train_lora.py

│   └── evaluate.py

│

├── tests/

│   ├── test_api.py

│   └── test_generation.py

│

├── generated_sites/

├── requirements.txt

├── .env.example

├── .gitignore

└── README.md

Training scripts optional hain. Initial MVP ko fine-tuning complete hone ka wait nahi karna chahiye.

4. AI Model Kaise Kaam Karega?

4.1 Model selection

Pretrained code model select karne ka reason ye hai ke model pehle hi programming patterns aur code generation seekh chuka hota hai.

Tumhara kaam model ko dobara basic HTML aur CSS sikhana nahi, balki uski capabilities ko apne product ke requirements ke mutabiq specialize karna hai.

Initial inference model:

Qwen2.5-Coder-3B-Instruct

Alternative:

Qwen2.5-Coder-7B-Instruct

Official model references:

- Qwen2.5-Coder: https://github.com/QwenLM/Qwen2.5-Coder

- Hugging Face model: https://huggingface.co/Qwen/Qwen2.5-Coder-3B-Instruct

Model license, redistribution conditions aur commercial-use permissions ko apni chosen model variant ke liye verify karna.

4.2 Model ko prompt kaise dena hai?

Raw user prompt ko directly model ko dene ke bajaye ek structured instruction use karo.

Example:

SYSTEM:

You are an expert HTML and CSS website generator.

RULES:

1. Generate valid HTML5.

2. Generate responsive CSS.

3. Do not use React or external build tools.

4. Keep HTML and CSS separate.

5. Use semantic HTML elements.

6. Include a mobile-friendly layout.

7. Do not include explanations inside the code.

8. Do not include server-side code.

9. Return the requested output in a defined format.

USER:

Create a modern portfolio website with a dark theme,

blue gradients, project cards, and a contact section.

Model ko output ka format bhi clearly specify karna hoga.

Example JSON output:

{

"html": "<!DOCTYPE html>...",

"css": "body { ... }"

}

Production implementation mein output ko parse aur validate karna hoga. Model ke JSON output par bina validation ke bharosa nahi karna chahiye.

4.3 Prompt enhancement

Future version mein ek separate prompt-planning step add kar sakte ho.

Example:

User prompt → Design specification → Code generation.

Design specification:

{

"website_type": "portfolio",

"theme": "dark",

"primary_color": "#2563eb",

"sections": [

"navbar",

"hero",

"projects",

"contact",

"footer"

],

"responsive": true

}

Isse model ko clear requirements milengi aur output ko test karna asaan hoga.

5. Data Kahan Se Aayega?

Ye project ka sabse important part hai.

AI model ko train ya fine-tune karne ke liye sirf HTML files ka collection enough nahi hota. Humein prompt aur uske corresponding high-quality output ke pairs chahiye.

5.1 Data sources

Source A — Apna manually created dataset

Sabse reliable initial source.

Khud HTML/CSS examples create karo:

- Portfolio websites

- Business landing pages

- Restaurant websites

- Agency websites

- Product landing pages

- SaaS websites

- Blog layouts

- Login/signup pages

- Pricing pages

- Contact pages

- Responsive navigation bars

Har example ke saath user prompt aur expected output store karo.

Source B — Open-source GitHub projects

GitHub par HTML/CSS templates aur projects mil sakte hain.

Source: https://github.com

Lekin public repository ka matlab automatically unrestricted training ya commercial use nahi hota.

Har dataset ke liye:

- License verify karo.

- Copyright aur attribution requirements follow karo.

- Personal information remove karo.

- Secrets aur API keys remove karo.

- Duplicate examples eliminate karo.

- Original source aur license metadata preserve karo.

Source C — Open-source website templates

Aise templates use karo jinki licenses tumhare intended use ko permit karti hon.

Har template ko dataset mein add karne se pehle check karo:

- License.

- HTML validity.

- CSS completeness.

- Responsive behavior.

- Broken image references.

- Code quality.

Source D — Synthetic dataset

Synthetic data ka matlab hai AI ki madad se naye prompt/code examples generate karna.

Example:

Prompt: "Create a responsive gym website with a black-and-orange theme."

Expected output: HTML + CSS.

Phir doosre prompts:

- "Make the hero section taller."

- "Change the theme to green."

- "Add three pricing cards."

- "Make the navbar mobile-friendly."

Generated examples ko automatically accept mat karna. Inko validation aur quality checks se pass karna zaroori hai.

Source E — User feedback

Future mein users ke consent ke saath:

- Original prompt

- Generated code

- User modifications

- Validation results

- Optional quality rating

collect kiye ja sakte hain.

Privacy policy aur data retention controls zaroor implement karna. Private prompts ko bina permission training data mein use mat karna.

6. Dataset Ka Format

Initial project mein JSONL format use karo.

Har line ek independent training example hogi.

Example:

{"prompt":"Create a blue portfolio website with three project cards.","html":"<!DOCTYPE html>...","css":"body { background: #0f172a; }"}

{"prompt":"Create a responsive restaurant landing page.","html":"<!DOCTYPE html>...","css":"body { font-family: Arial; }"}

Real examples mein complete HTML aur CSS content hona chahiye; upar sirf format samjhane ke liye abbreviated code use hua hai.

Better training format

Agar instruction-tuning kar rahe ho, to structured messages format use kar sakte ho:

{

"messages": [

{

"role": "system",

"content": "Generate valid responsive HTML and CSS."

},

{

"role": "user",

"content": "Create a responsive portfolio website."

},

{

"role": "assistant",

"content": "{\"html\":\"...\",\"css\":\"...\"}"

}

]

}

Apne training pipeline ke mutabiq ek format choose karo aur consistent raho.

6.1 Kitna data chahiye?

Initial MVP ke liye:

| Phase | Target examples |
| --- | --- |
| Initial manually reviewed examples | 50–100 |
| MVP evaluation prompts | 30–50 |
| First fine-tuning dataset | 500–1,000 |
| Improved dataset | 2,000–5,000+ |

Ye planning targets hain, guaranteed minimums nahi. Achhe examples ki quality, diversity aur correctness sirf quantity se zyada important ho sakti hai.

Agar 30 din mein 500 high-quality examples collect nahi ho paate, to fine-tuning delay kar do aur pretrained model ke saath MVP complete karo.

6.2 Dataset splitting

Dataset ko teen separate groups mein divide karo:

- Training: approximately 80%

- Validation: approximately 10%

- Test: approximately 10%

Closely related duplicates ko different groups mein distribute mat karna. Warna evaluation artificially achhi nazar aa sakti hai.

7. Kya Apna Model Scratch Se Train Karna Chahiye?

Pehle month mein nahi.

Foundation model ko scratch se train karne ke liye large-scale training data, substantial compute, model-training expertise aur evaluation infrastructure chahiye.

Tumhare project ke liye teen stages honi chahiye:

Stage 1 — Existing model

Prompt engineering aur local inference se functional product banao.

Stage 2 — Fine-tuning

Apne reviewed prompt/code dataset par LoRA/QLoRA try karo, jab hardware aur dataset ready ho.

Stage 3 — Specialized model

Fine-tuned model ko base model ke against benchmark karo. Agar meaningful improvement milti hai tab usko production pipeline mein use karo.

Fine-tuning se har task par automatically improvement ki guarantee nahi hoti. Isliye before-and-after evaluation zaroori hai.

Training reference: https://huggingface.co/docs/peft

8. Model Ko Test Kaise Karna Hai?

Har prompt ke baad sirf ye dekhna enough nahi ke code generate ho gaya.

Quality evaluation mein ye checks hon:

- HTML parse ho raha hai ya nahi.

- CSS valid hai ya nahi.

- Preview render ho rahi hai ya nahi.

- Mobile viewport par layout sahi hai ya nahi.

- Prompt ki requested sections maujood hain ya nahi.

- Images aur links broken to nahi.

- Code generation fail to nahi hui.

- Generated website unsafe behavior to nahi rakhti.

Suggested initial test suite:

- 10 portfolio prompts.

- 10 business website prompts.

- 10 restaurant prompts.

- 10 responsive layout prompts.

- 10 modification prompts.

Har test ko same prompts par base model aur fine-tuned model ke against run karo.

Important metrics:

- Successful generation rate.

- HTML/CSS validation rate.

- Browser rendering success rate.

- Requirement completion rate.

- Average generation time.

- Manual design quality score.

Target metrics ko goals samjho, guaranteed outcomes nahi.

9. Security Requirements

Generated code ko browser mein render karna security-sensitive hai.

Minimum requirements:

- Preview ko sandboxed iframe mein run karo.

- Generated HTML ko main application DOM mein directly inject mat karo.

- JavaScript execution ko initial MVP mein disable rakho.

- Sensitive browser capabilities restrict karo.

- Untrusted generated files ko backend server par execute mat karo.

- API keys frontend code mein expose mat karo.

- User inputs aur outputs ke size limits rakho.

- Production deployment mein rate limits aur authentication add karo.

- External network access ko preview ke liye restrict ya carefully control karo.

Generated code ko preview karne ke liye sandbox configuration ko browser security requirements ke mutabiq test karna hoga.

10. Complete 30-Day Development Plan

Week 1 — Foundation aur Model Setup

Day 1 — Requirements final karo

- Project scope define karo.

- Features ki list banao.

- HTML/CSS-only MVP fix karo.

- Sample prompts likho.

- Git repository create karo.

Deliverable: Project specification aur initial repository.

Day 2 — Hardware aur environment check

- Windows version check karo.

- RAM aur GPU/VRAM identify karo.

- Python environment setup karo.

- Git install aur configure karo.

- Model runtime ki installation verify karo.

Deliverable: Working development environment.

Day 3 — Base model setup

- Qwen2.5-Coder-Instruct ka suitable size choose karo.

- Local inference setup karo.

- Ek basic coding prompt run karo.

- HTML output save karo.

- Model ki response quality inspect karo.

Deliverable: Model se pehla HTML output.

Day 4 — CSS generation test

- HTML aur CSS separately generate karwao.

- Responsive layout prompts test karo.

- Output consistency check karo.

- Generation errors document karo.

Deliverable: HTML/CSS generation experiment.

Day 5 — Prompt engineering

- System instructions likho.

- Output format define karo.

- HTML/CSS separation enforce karo.

- Responsive design requirements add karo.

- Malformed output cases test karo.

Deliverable: Initial prompt template.

Day 6 — Dataset creation

- 20–30 prompt/code examples prepare karo.

- Website categories define karo.

- Examples manually review karo.

- JSONL structure implement karo.

Deliverable: First dataset.

Day 7 — Week 1 review

- 10 sample prompts run karo.

- Successful generations count karo.

- Common failures note karo.

- Agle week ke tasks prioritize karo.

Deliverable: Baseline model report.

Week 2 — Backend aur Frontend

Day 8 — FastAPI backend

- Python API project setup karo.

- Health endpoint create karo.

- Prompt generation endpoint implement karo.

- Request/response schemas define karo.

Deliverable: Working backend API.

Day 9 — Model integration

- Backend ko local inference engine se connect karo.

- Prompt model ko forward karo.

- Generated result return karo.

- Timeout aur exception handling add karo.

Deliverable: API se HTML/CSS generation.

Day 10 — Frontend design

- Prompt textarea banao.

- Generate button add karo.

- Loading state implement karo.

- Error messages show karo.

- Basic responsive UI create karo.

Deliverable: Frontend prototype.

Day 11 — Frontend/backend connection

- Fetch API implement karo.

- Backend response parse karo.

- Generated HTML/CSS display karo.

- Network errors handle karo.

Deliverable: End-to-end generation flow.

Day 12 — Code editor

- Monaco Editor ya CodeMirror integrate karo.

- HTML aur CSS ke separate tabs banao.

- Syntax highlighting enable karo.

- Code editing support add karo.

Deliverable: Editable source code.

Day 13 — Live preview

- Sandboxed iframe create karo.

- HTML/CSS preview pipeline implement karo.

- Mobile/desktop viewport switching add karo.

- Unsafe preview behavior test karo.

Deliverable: Live website preview.

Day 14 — Download functionality

- HTML download implement karo.

- CSS download implement karo.

- Generated filenames set karo.

- Downloaded files browser mein test karo.

Deliverable: First usable AI website builder.

Week 3 — Data, Quality aur Model Improvement

Day 15 — Prompt categories expand karo

- Portfolio.

- Business landing page.

- Restaurant.

- Agency.

- SaaS landing page.

Har category ke liye multiple prompt styles prepare karo.

Deliverable: Diverse prompt collection.

Day 16 — Dataset cleaning

- Broken examples remove karo.

- Duplicate examples identify karo.

- License metadata record karo.

- Output format standardize karo.

Deliverable: Clean dataset v1.

Day 17 — Automated validation

- HTML parser integrate karo.

- CSS validation tool add karo.

- Empty outputs detect karo.

- Invalid output errors log karo.

Deliverable: Code quality checks.

Day 18 — Browser testing

- Browser automation setup karo.

- Generated website load karwao.

- Console errors capture karo.

- Desktop aur mobile viewport test karo.

Deliverable: Browser-based test suite.

Day 19 — Fine-tuning feasibility

- GPU/VRAM check karo.

- Dataset quality assess karo.

- LoRA/QLoRA configuration plan karo.

- Training dependencies verify karo.

Deliverable: Fine-tuning decision report.

Day 20 — Optional fine-tuning experiment

Agar sufficient hardware aur clean dataset available ho:

- Base model load karo.

- Small training experiment run karo.

- Training loss monitor karo.

- Checkpoint save karo.

Agar hardware insufficient ho, is task ko skip karo aur inference improvements par kaam karo.

Deliverable: Optional experimental adapter.

Day 21 — Model comparison

- Same test prompts base model par run karo.

- Fine-tuned model par same prompts run karo.

- Validation rates compare karo.

- Visual results compare karo.

Deliverable: Model comparison report.

Week 4 — Product Features aur Release

Day 22 — Prompt-based editing

Example:

"Change the primary color to purple."

- Existing HTML/CSS context model ko pass karo.

- Modification instruction include karo.

- Updated code return karo.

- Previous version preserve karo.

Deliverable: Iterative editing.

Day 23 — Better layouts

- Reusable design instructions add karo.

- Typography consistency improve karo.

- Spacing requirements add karo.

- Accessible HTML patterns encourage karo.

Deliverable: Improved design quality.

Day 24 — Error recovery

- Invalid JSON recovery.

- Empty response handling.

- Timeout handling.

- Retry logic.

- Error logging.

Deliverable: More reliable generation flow.

Day 25 — Security review

- Iframe sandbox verify karo.

- API secrets inspect karo.

- Input/output limits add karo.

- Unsafe generated code cases test karo.

Deliverable: Security checklist.

Day 26 — User experience

- Clear progress indicators.

- Copy code buttons.

- Reset prompt button.

- Better error messages.

- Responsive dashboard.

Deliverable: Improved interface.

Day 27 — Complete regression testing

- Full prompt suite run karo.

- HTML/CSS validation run karo.

- Preview failures identify karo.

- Downloaded files test karo.

Deliverable: Regression test report.

Day 28 — Documentation

- Installation instructions.

- Environment setup.

- Model setup.

- API documentation.

- Dataset format.

- Known limitations.

Deliverable: README aur developer guide.

Day 29 — Deployment preparation

- Environment variables configure karo.

- Production server setup plan karo.

- Model hosting requirements estimate karo.

- Logs aur rate limits configure karo.

Deliverable: Deployment-ready candidate.

Day 30 — Final release

- Final smoke tests run karo.

- 10–20 representative prompts demo karo.

- Known issues document karo.

- Git release tag create karo.

- Next version roadmap prepare karo.

Deliverable: AI Website Builder v1.0 MVP.

11. Day 30 Par Expected Result

Agar daily consistent development hoti hai, to target ye hona chahiye:

- Working prompt-based website generator.

- Local code model integration.

- HTML/CSS code output.

- Browser preview.

- Code editor.

- Downloadable website files.

- Basic prompt-based editing.

- Dataset pipeline.

- Evaluation scripts.

- Installation documentation.

Fine-tuned model, advanced visual quality aur public deployment hardware, dataset aur development progress par depend karenge.

12. Initial Budget and Hardware

Budget ko do parts mein divide karo.

Local development:

- Existing Windows PC.

- Python aur Git.

- Open-source model.

- Local inference runtime.

- Free code editor.

- Local browser preview.

Possible paid expenses:

- Cloud GPU for fine-tuning.

- Hosted inference API.

- Domain name.

- Cloud hosting.

- Persistent storage.

Agar local PC par model smoothly nahi chalta, to pehle hosted inference ya cloud compute use karna zyada practical ho sakta hai. GPU khareedna shuru mein zaroori nahi.

Exact hardware requirement selected model, quantization, context length aur runtime par depend karegi.

13. Future Versions

Version 1.0: HTML + CSS website generator.

Version 1.1: JavaScript generation and interactive components.

Version 1.2: Prompt-based editing aur multiple-page websites.

Version 2.0: React/Tailwind website generation.

Version 2.1: Automatic screenshot testing aur visual improvements.

Version 3.0: Full-stack projects, APIs aur database integration.

Version 4.0: Hosted SaaS platform with user accounts, project history aur paid plans.

14. Final Recommendation

Project ko teen parallel tracks mein develop karo:

- Product: Frontend, backend, preview aur downloads.

- Model: Prompt engineering, model evaluation aur optional fine-tuning.

- Data: High-quality examples, validation aur test datasets.

Sabse pehle ek reliable generator banao. Uske baad data collect karo, quality measure karo aur phir fine-tuning par invest karo.

Is approach se tum sirf model train karne ke bajaye ek usable AI product develop karoge.

Initial project name: AI Website Builder — HTML/CSS Model v1.0.

First milestone: Ek prompt do aur browser mein working website preview hasil karo.

Data kahan se download karna hai?

1. GitHub — HTML/CSS website templates

Portfolio, business, restaurant aur landing pages ke original source code.

12 free HTML/CSS templates · MIT-licensed repository.

GitHub

2. MDN Web Docs — HTML/CSS examples

HTML tags, CSS styling, responsive layouts aur web development ke examples seekhne aur test karne ke liye.

MDN learning-area repository · Official tutorials.

GitHub

+1

3. Hugging Face — Pretrained AI model

Qwen model weights aur model documentation. Ye website templates ka dataset nahi, balki tumhara starting AI model hai.

Qwen2.5-Coder-3B-Instruct.

4. Open-source template collections

Different industries ke liye zyada website layouts aur design examples.

120+ template collection · Har individual template ka license aur usage conditions verify karna.

GitHub

2. In data ko apne model ke liye kaise use karna hai?

Ye workflow follow karo:

Source code collect karo

GitHub templates + apne HTML/CSS examples

Clean aur validate karo

License check, duplicate removal, HTML/CSS testing

Prompt + code pairs banao

JSONL dataset

Qwen model ko evaluate karo

Pehle existing model; phir zaroorat par fine-tuning

3. Example: apna dataset kaisa dikhega?

{

"prompt": "Create a responsive portfolio website with a dark theme",

"html": "<!DOCTYPE html> ...",

"css": "body { background: #111827; } ..."

}

Har record mein complete, tested HTML/CSS code hona chahiye. Upar abbreviated example sirf format samjhane ke liye hai.

Important: Har template ko automatically AI training data mat samajhna. Uska license, code quality aur prompt ke saath matching check karna zaroori hai.

4. Tumhare liye best starting strategy

- Pehle: 20–30 licensed templates collect karo.

- Phir: Har template ke liye 2–3 accurate prompts aur expected outputs banao.

- Uske baad: 50–100 reviewed examples se apni initial dataset pipeline test karo.

- Finally: Qwen model se 30–50 alag prompts generate karwa ke results compare karo. Quality mein improvement ki zaroorat ho to dataset expand karke fine-tuning test karo.

Ek aur zaroori baat: dataset se model automatically train nahi hota. Dataset prepare karna, fine-tuning run karna aur trained model ko evaluate karna alag steps hain.

Agar tum Windows PC par kaam kar rahe ho, agla practical step GitHub se templates download karke unhein data/raw/ folder mein organize karna hai. Uske baad hum Python script bana sakte hain jo HTML/CSS files scan kare aur dataset prepare kare.